## Slide 1
MITCHELL PARK DEVELOPMENT Club Presentation 2021

## Slide 2
MITCHELL PARK DEVELOPMENT PRESENTATION
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
2
SEEKING CLUB APPROVAL FOR PROJECT TO PROCEED:
PROJECT SCOPE
  Pavilion & parking solution (strengthening & access)
  Indoor court structure solution
DESIGN SOLUTION
STAGED BUILD APPROACH
BUDGET & FINANCIAL AUTHORITY
COUNCIL FUNDING CONDITIONS
PROJECT TERMS OF REFERENCE
PROJECT MANAGEMENT STRUCTURE
PROJECT SCHEDULE

## Slide 3
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
3
1. PROJECT SCOPE
  The following slide outlines the parameters of the project and the plan to address the key strategic issues facing HVT.

## Slide 4
  1. PROJECT SCOPE: ADDRESS 2 STRATEGIC ISSUES
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
4
  Patron Safety and Access
    = Pavilion Upgrade and Parking
    earthquake strengthening & improved access
Financial Sustainability
  = Indoor Court Structure
    increased revenue via court/facility hire
    all weather play, iconic structure

## Slide 5
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
5
2. DESIGN SOLUTION
  The Mitchell Park Development Group seek approval to proceed with delivering the facility upgrades illustrated in the following visuals.

## Slide 6
  2. DESIGN SOLUTION: FUNDING MODEL IMPACT
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
6
  A new funding model was required due to changes in Council funding priorities, the COVID emergency and build industry cost escalation
    The new funding model developed in partnership by HCC/HVT will require an alteration to our overall Mitchell Park site plan
Core funding will now be secured via the sale of a small component of Mitchell Park reserve status land requiring an adjustment by Council to our lease
Upon HVT full support of the plan the Council will engage in a revocation process to change the designated land area title so it can be sold
Net proceeds from the land sale will be passed onto HVT by HCC to help fund our project

## Slide 7
  2. DESIGN SOLUTION: MITCHELL PARK SITE PLAN
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
7
Revocation and sale of reserve land
  Approximately 1,600sqm of land will be sold to the neighboring Hutt Valley Health Centre
  The HVT leased land to be sold consists of the tennis Court 4 carpark plus most of tennis Courts 9 and 13 (Green area)
  Net proceeds from the sale towards our development is estimated at $1.25m
  Our lease will be adjusted to reinstate 1 tennis court in the South-east corner taking the total court count back to 12

## Slide 8
2. DESIGN SOLUTION: CURRENT PAVILION
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
8

## Slide 9
2. DESIGN SOLUTION: PAVILION
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
9

## Slide 10
2. DESIGN SOLUTION: PAVILION/COURTS
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
10

## Slide 11
2. DESIGN SOLUTION: MITCHELL PARK SITE
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
11
Edit visual to show land title change…

## Slide 12
2. DESIGN SOLUTION: PAVILION/PARKING/INDOOR COURTS
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
12

## Slide 13
2. DESIGN SOLUTION: PAVILION FOYER
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
13

## Slide 14
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
14
2. DESIGN SOLUTION: INDOOR COURT STRUCTURE

## Slide 15
2. DESIGN SOLUTION: INDOOR COURT STRUCTURE
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
15

## Slide 16
2. DESIGN SOLUTION: INDOOR COURT STRUCTURE
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
16

## Slide 17
2. DESIGN SOLUTION: MITCHELL PARK SITE
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
17
Edit visual to show land title change…

## Slide 18
2. DESIGN SOLUTION: MITCHELL PARK SITE
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
18

## Slide 19
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
19
3. STAGED BUILD APPROACH
  Changes in Council funding priorities, COVID and cost escalation across the construction industry has forced changes to how we deliver the plan.

## Slide 20
  3. STAGED BUILD APPROACH
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
20
  The Development Group recommends a staged build plan
    Stage 1: Indoor Court structure
    Stage 2: Pavilion earthquake strengthening
      Upgrade Pavilion to be code compliant (Council funding requirement)
      The approach will reduce the risk of cost escalation and provide additional time to raise funds for the Pavilion Upgrade
      Non-essential build components will be deferred until required funding is secured
      Internal Pavilion refit works to improve access
      New Tennis Court 9 (12th Court)
      Re-instating floodlights to Tennis Courts 8 and 12

## Slide 21
  3. STAGED APPROACH: STAGE 1 - INDOOR COURTS
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
21
  Prioritising the indoor court build will reduce cost escalation risk as it represents 80% of the total project budget.
    The Indoor Courts will significantly increase revenue streams via new court hire and sponsorship opportunities
      Private hire, coaching, small format tournaments, leagues, birthdays, tennis aerobics
      Improved business house competitions that can run uninterrupted year-round
      Iconic structure that will increase the profile of tennis and services offered at the site that can be leveraged e.g. new sponsorship, commercial or future partner relationships
    New revenue streams will help with HVT fundraising efforts for the Pavilion redesign

## Slide 22
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
22
4. BUDGET AND FINANCIAL AUTHORITY
  Mitchell Park Development Committee is seeking Club approval for the project approach and financial authority to deliver the plan.

## Slide 23
STAGE 1 & 2: FUNDING PLAN | $
Hutt Valley Tennis (Development Fund) | $ 450,000
Hutt City Council Funds | $ 500,000
Health Hub Land Sale (Developer) | $ 1,250,000
Hutt Valley Tennis (Grants, Sponsors & Fundraising) | $ 370,000
TOTAL | $ 2,570,000
STAGE 1 & 2: DESIGN & BUILD BUDGET | $
Indoor Tennis Court Structure | $ 1,700,000
Groundworks (Playing Surface & Car Parking) | $ 350,000
Pavilion Strengthening & Access | $ 450,000
Professional Fees & Contingency | $ 70,000
* Lights Installation - Courts 8 & 12 | $ 60,000*
* New Court 9 (Lights & Fencing) | $ 120,000*
TOTAL | $ 2,570,000
  4. BUDGET: STAGES 1 & 2
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
23
    *Deferred works due to funding shortfall
    HVT fundraising requirement
    Approximate net land sale funds for HVT
    HCC Grant – conditional to delivery of project
    HVT Savings available for MP Development
    Tight budget: Indoor Courts: turn-key solution, Pavilion: structural upgrades & access only

## Slide 24
  4. BUDGET: STAGED PLAN
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
24
STAGE 1. INDOOR COURT BUDGET | $
Indoor Tennis Court Structure | $ 1,700,000
Groundworks (Playing Surface) | $ 220,000
Groundworks (Car Parking) | $ 130,000
Professional Fees | $ 10,000
Contingency | $ 20,000
TOTAL* | $ 2,080,000
STAGE 2. PAVILION DESIGN & BUILD BUDGET | $
Pavilion Strengthening & Access | $ 450,000
Professional Fees | $ 20,000
Contingency | $ 20,000
TOTAL* | $ 490,000
*Total Funds available to HVT if MP land sale is successful & HCC funds released: = $ 2,200,000
*Minimum HVT fundraising required to strengthen pavilion = $ 370,000

## Slide 25
  4. BUDGET: FUNDING MODEL
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
25
PROJECT FUNDING | FUNDING TARGETS |  | FUNDING PLAN
HVT (Development Fund) | $ 450,000 |  | HVT asset replacement funds set aside and ready for use
Hutt City Council (Grant) | $ 500,000 |  | Hutt City Council grant approved for HVT use
Health Hub Land Sale (Developer) | $ 1,250,000 |  | Approx. net proceeds from proposed MP land sale consisting of tennis courts 9, 13 and the tennis court 4 car park.
HVT (Sponsors & Fundraising) | $ 170,000 |  | Mixed model approach - naming rights, private sponsorship, fundraising events, signage, business, private donations.
HVT (Grant Organisations) | $ 200,000 |  | Community grant organisations, NZ lotteries
TOTAL | $ 2,570,000 |  | 
O
O
  Upon Club support of the plan the Development Group will commence its fundraising plans to raise the funding shortfall of $370k
    The fundraising plan will be extensive with funds sought via multiple channels
    Every attempt will be made to secure funds via non-competing club sources
O
O

## Slide 26
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
26
5. COUNCIL FUNDING CONDITIONS
  Mitchell Park Development Committee are seeking Association approval for the group to work with Council representatives to deliver the plan and the most desirable outcome for HVT.

## Slide 27
  5. COUNCIL FUNDING CONDITIONS
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
27
  Total funding contributions from HCC consist of:
    $500k financial grant
    $1.25m being the approximate net proceeds from the land sale
  Formal approval of a final design concept
  Evidence and comfort regarding the budget to deliver the Indoor Court Structure and Pavilion steel upgrades, and confirmed or committed fundraising
  Evidence and comfort of the construction programme and methodology
  Formal approval of a project governance structure
  A senior Council Officer sitting on an appropriate Project Control Group
  Formal approval of a business case that demonstrates the ongoing operational sustainability and maintenance of the facility by HVT

## Slide 28
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
28
6. PROJECT TERMS OF REFERENCE
  The following slide details the parameters of the project and outlines the roles and responsibilities of the team and how it will function.

## Slide 29
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
29
Role The Mitchell Park Development Group (MPDG) will be responsible for providing management direction to the project developing indoor tennis courts and pavilion earthquake strengthening at Mitchell Park Racquet Centre; including all decisions to execute the project; issue and risk resolution, allocation of resource (financial and people) and stakeholder management. This will be a decision making working committee that has the mandate to approve all decisions within agreed scope, budget and schedule to deliver the outcome. All key decisions and actions will be minuted. | Membership The committee membership and administrative requirements are as follows: Members > Gary Baird - Chairperson > Phil Fisher > Shane Jackson > Gary Naylor > Grahame Boyd > Finance controller (TBD) > Brendon Smith > Hutt City Council delegate (TBD) Guests To be confirmed for each meeting, within the context of the agenda. The working committee may be supported by a coordinator. Additional attendees may be required to attend on an ad-hoc basis. Quorum: Chair + 4 voting members (60%) Frequency: proposed monthly The chair may add additional members to the committee as needed Projects dimensions Scope: Indoor Court Structure and Pavilion as outlined in council submission Budget $2.57m Build Schedule: Stage 1: all preparation by Jun 2021; project delivery by Nov 2021 Stage 2: all preparation by March 2022, project delivery by Nov 2022
Responsibilities To secure the grant and sponsorship funding as outlined in the submission. To make decisions required by the project, within agreed delegated authorities, scope and schedule. To assist all project workstreams with external stakeholder engagement. To assist the workstreams to resolve issues and risks. The council representative needs to carry full authority to endorse all decisions on behalf of council to meet the requirement as set out by the council decision. | 
  6. PROJECT TERMS OF REFERNCE

## Slide 30
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
30
7. PROJECT MANAGEMENT STRUCTURE
  The following project structure is proposed. Key resources will be invited to join project groups when expertise is required or deemed beneficial.

## Slide 31
  7. PROJECT MANAGEMENT STRUCTURE
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
31
HVT MANAGEMENT COMMITTEE
MP DEVELOPMENT COMMITTEE
FUNDRAISING & SPONSORSHIP GROUP
PAVILION / ACCESS & GROUNDS GROUP
INDOOR COURT STRUCTURE GROUP
Gary Baird - Committee Chair
Shane Jackson
Grahame Boyd
Brendon Smith
Phil Fisher
Gary Naylor
Finance controller (TBD)
Hutt Council delegate (TBD)
.......... ..............
.......... ..............
.......... ..............
.......... ..............
.......... ..............
.......... ..............
.......... ..............
.......... ..............
.......... ..............
.......... ..............
.......... ..............
.......... ..............

## Slide 32
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
32
8. PROJECT SCHEDULE
  The Development Group is motivated to move quickly on the project in an aim to mitigate risks around cost escalation and in an aim to deliver new revenue streams for HVT.

## Slide 33
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
33
HCC MP Land Revocation
SGM - Club Project Vote
Build
  8. PROJECT SCHEDULE
Indoor Court Final Design
Land revocation work
Quotes, final pricing & consent
Grants, sponsors, donors
Indoor Court Fundraising
Indoor Court & Parking Build
Council Funding Conditions
Indoor Court Operating Model
HCC approval
INDOOR COURT BUILD
New operating model developed & implemented
2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  | 
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
STAGE ONE INDOOR PLAN
STAGE TWO PAVILION PLAN
Pavilion Re-Design Plan
Pavilion Structural Upgrade
Architectural plans & final design
Structural engineer plans & final design
Quotes, QS, final pricing & consent
Pavilion Final Design & Quotes
Pavilion Upgrade Build
Pavilion Fundraising Plan
PAVILION UPGRADE BUILD
New operating model developed & implemented
Grants, sponsors, donors, naming rights
Facility Operating Model

## Slide 34
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
34
9. SPECIAL GENERAL MEETING
  A nominated delegate from each Club will be asked to vote on one of two motions at a SGM set for 7pm, Friday, 26 Feb 2021.

## Slide 35
  9. SPECIAL GENERAL MEETING: NEXT STEPS
MITCHELL PARK DEVELOPMENT
Club Presentation 2021
35
  Clubs are being asked to vote for one of the below motions:
    Support the Mitchell Park Development Plan:
      this decision will enable the project to proceed
    Oppose the Mitchell Park Development Plan:
        this decision will stop the project and see Council plus Developer funding lost